## Sheet1
Sprint | From | To | As a/an | I/we want to… | so that… | Priority | Status
0 | May 9 | May 16 | student | enter known variables | the calculator can produce as many unknowns as possible | Required | To Do
|  |  | developer | create a list of variables | I can decide which equations this software will solve |  | To Do
|  |  | developer | set up GitHub/Trello, etc. | so our team can communicate and share files |  | To Do
|  |  | developer | create an algorythm | I can solve for missing equations |  | To Do
|  |  | developer | use recursion | to make a better algorythm for solving multiple unknowns |  | To Do
|  |  | team | create a catchy name for the app | I can market it to students |  | To Do
|  |  | product owner / scrum master | set up the sprint schedule | I can delegate tasks and make sure we are on track |  | To Do
|  |  | developer | list references and sources | so that I give credit to those who created any code we use |  | To Do
0 | May 9 | May 16 | student | visually interact with the software | I can more easily enter the unkowns | Requred | To Do
|  |  | developer | create a user friendly GUI | students can easily use the software |  | To Do
0 | May 9 | May 16 | student | have a user manual | to help with any questions I have with the software | Nice to have | To Do
0 | May 9 | May 16 | student | enter units | I don't have to do unit conversion myself | Nice to have | To Do
0 | May 9 | May 16 | student | enter variables from many disciplines | I can gain assistance with a broader range of physics problems | Nice to have | To Do
1 | May 17 | May 23 | student | enter known variables | the calculator can produce as many unknowns as possible | Required | In Progress
|  |  | developer | use recursion | to make a better algorythm for solving multiple unknowns |  | To Do
|  |  | team | create a presentation | for Midterm I |  | In Pogress
|  |  | developer | create a list of variables | I can decide which equations this software will solve |  | In Pogress
|  |  | developer | create an algorythm | I can solve for missing equations |  | In Progress
|  |  | team | create a catchy name for the app | I can market it to students |  | In Progress
|  |  | product owner / scrum master | set up the sprint schedule | I can delegate tasks and make sure we are on track |  | In Progress
|  |  | developer | list references and sources | so that I give credit to those who created any code we use |  | In Progress
|  |  | developer | set up GitHub/Trello, etc. | so our team can communicate and share files |  | Done
1 | May 17 | May 23 | student | visually interact with the software | I can more easily enter the unkowns | Requred | In Progress
|  |  | developer | create a user friendly GUI | students can easily use the software |  | In Progress
2 | May 24 | June 6 | student | enter known variables | the calculator can produce as many unknowns as possible | Required | In Progress
|  |  | developer | create a list of variables | I can decide which equations this software will solve |  | In Pogress
|  |  | developer | create an algorythm | I can solve for missing equations |  | In Progress
|  |  | team | create a catchy name for the app | I can market it to students |  | In Progress
|  |  | developer | list references and sources | so that I give credit to those who created any code we use |  | In Progress
|  |  | product owner / scrum master | set up the sprint schedule | I can delegate tasks and make sure we are on track |  | Done
|  |  | team | create a presentation | can succeed on Midterm I |  | Done
|  |  | developer | set up GitHub/Trello, etc. | so our team can communicate and share files |  | Done
|  |  | developer | use recursion | to make a better algorythm for solving multiple unknowns |  | Dropped
2 | May 24 | June 6 | student | visually interact with the software | I can more easily enter the unkowns | Requred | In Progress
|  |  | developer | create a user friendly GUI | students can easily use the software |  | In Progress
|  |  | developer | create a method to save entries | students can easily reuse the same variable values |  | Done
|  |  | developer | create a menu bar | students can save their projects, access credits, help, etc. |  | Done
2 | May 24 | June 6 | student | have a user manual | I can gain assistance with a broader range of physics problems | Nice to have | In Progress
|  |  | developer | create a help page / menu | students can learn how the software works |  | In Progress
3 | June 7 | June 20 | student | enter known variables | the calculator can produce as many unknowns as possible | Required | In Progress
|  |  | developer | create a list of variables | I can decide which equations this software will solve |  | In Pogress
|  |  | developer | create an algorythm | I can solve for missing equations |  | In Progress
|  |  | team | create a catchy name for the app | I can market it to students |  | In Progress
|  |  | developer | list references and sources | so that I give credit to those who created any code we use |  | In Progress
|  |  | product owner / scrum master | set up the sprint schedule | I can delegate tasks and make sure we are on track |  | Done
|  |  | team | create a presentation | can succeed on Midterm I |  | Done
|  |  | developer | set up GitHub/Trello, etc. | so our team can communicate and share files |  | Done
|  |  | developer | use recursion | to make a better algorythm for solving multiple unknowns |  | Dropped
3 | June 7 | June 20 | student | visually interact with the software | I can more easily enter the unkowns | Requred | In Progress
|  |  | developer | create a user friendly GUI | students can easily use the software |  | In Progress
Items added
Items removed