## Sheet1
Sprint | From | To | As a/an | I/we want to… | so that… | Notes | Priority | Status
0 | 2019-05-09 | 2019-05-16 | student | enter known variables | the calculator can produce as many unknowns as possible |  | Required | To Do
|  |  | developer | create a list of variables | I can decide which equations this software will solve |  |  | To Do
|  |  | developer | set up GitHub/Trello, etc. | so our team can communicate and share files |  |  | To Do
|  |  | developer | create an algorythm | I can solve for missing equations |  |  | To Do
|  |  | developer | use recursion | to make a better algorythm for solving multiple unknowns |  |  | To Do
|  |  | team | create a catchy name for the app | I can market it to students |  |  | To Do
|  |  | product owner / scrum master | set up the sprint schedule | I can delegate tasks and make sure we are on track |  |  | To Do
|  |  | developer | list references and sources | so that I give credit to those who created any code we use |  |  | To Do
0 | 2019-05-09 | 2019-05-16 | student | visually interact with the software | I can more easily enter the unkowns |  | Requred | To Do
|  |  | developer | create a user friendly GUI | students can easily use the software |  |  | To Do
0 |  |  | student | have a user manual | to help with any questions I have with the software |  | Nice to have | To Do
0 |  |  | student | enter units | I don't have to do unit conversion myself |  | Nice to have | To Do
0 |  |  | student | enter variables from many disciplines | I can gain assistance with a broader range of physics problems |  | Nice to have | To Do
1 | 2019-05-17 | 2019-05-23 | student | enter known variables | the calculator can produce as many unknowns as possible |  | Required | In Progress
|  |  | developer | use recursion | to make a better algorythm for solving multiple unknowns |  |  | To Do
|  |  | team | create a presentation | for Midterm I |  |  | In Pogress
|  |  | developer | create a list of variables | I can decide which equations this software will solve |  |  | In Pogress
|  |  | developer | create an algorythm | I can solve for missing equations |  |  | In Progress
|  |  | team | create a catchy name for the app | I can market it to students |  |  | In Progress
|  |  | product owner / scrum master | set up the sprint schedule | I can delegate tasks and make sure we are on track |  |  | In Progress
|  |  | developer | list references and sources | so that I give credit to those who created any code we use |  |  | In Progress
|  |  | developer | set up GitHub/Trello, etc. | so our team can communicate and share files |  |  | Done
1 | 2019-05-17 | 2019-05-23 | student | visually interact with the software | I can more easily enter the unkowns |  | Requred | In Progress
|  |  | developer | create a user friendly GUI | students can easily use the software |  |  | In Progress
2 | 2019-05-24 | 2019-06-06 | student | enter known variables | the calculator can produce as many unknowns as possible |  | Required | In Progress
|  |  | developer | use recursion | to make a better algorythm for solving multiple unknowns |  |  | To Do
|  |  | developer | create a list of variables | I can decide which equations this software will solve |  |  | In Pogress
|  |  | developer | create an algorythm | I can solve for missing equations |  |  | In Progress
|  |  | team | create a catchy name for the app | I can market it to students |  |  | In Progress
|  |  | product owner / scrum master | set up the sprint schedule | I can delegate tasks and make sure we are on track |  |  | In Progress
|  |  | developer | list references and sources | so that I give credit to those who created any code we use |  |  | In Progress
|  |  | team | create a presentation | can succeed on Midterm I |  |  | Done
|  |  | developer | set up GitHub/Trello, etc. | so our team can communicate and share files |  |  | Done
2 | 2019-05-24 | 2019-06-06 | student | visually interact with the software | I can more easily enter the unkowns |  | Requred | In Progress
|  |  | developer | create a user friendly GUI | students can easily use the software |  |  | In Progress
3 | 2019-06-07 | 2019-06-20 | student | enter known variables | the calculator can produce as many unknowns as possible |  | Required | In Progress
|  |  | developer | use recursion | to make a better algorythm for solving multiple unknowns |  |  | To Do
|  |  | developer | create a list of variables | I can decide which equations this software will solve |  |  | In Pogress
|  |  | developer | create an algorythm | I can solve for missing equations |  |  | In Progress
|  |  | team | create a catchy name for the app | I can market it to students |  |  | In Progress
|  |  | product owner / scrum master | set up the sprint schedule | I can delegate tasks and make sure we are on track |  |  | In Progress
|  |  | developer | list references and sources | so that I give credit to those who created any code we use |  |  | In Progress
|  |  | team | create a presentation | can succeed on Midterm I |  |  | Done
|  |  | developer | set up GitHub/Trello, etc. | so our team can communicate and share files |  |  | Done
3 | 2019-06-07 | 2019-06-20 | student | visually interact with the software | I can more easily enter the unkowns |  | Requred | In Progress
|  |  | developer | create a user friendly GUI | students can easily use the software |  |  | In Progress