## Sheet1
| Task # | Developer | As a/an | I/we want to… | so that… | Priority
Sprint 0 - May 9 to May 16 |  |  | student | enter known variables | the calculator can produce as many unknowns as possible | Required
|  |  | developer | create a list of variables | I can decide which equations this software will solve | To Do
|  |  | developer | set up GitHub/Trello, etc. | so our team can communicate and share files | To Do
|  |  | developer | create an algorithm | I can solve for missing equations | To Do
|  |  | developer | use recursion | to make a better algorithm for solving multiple unknowns | To Do
|  |  | team | create a catchy name for the app | I can market it to students | To Do
|  |  | PO / SM | set up the sprint schedule | I can delegate tasks and make sure we are on track | To Do
|  |  | developer | list references and sources | so that I give credit to those who created any code we use | To Do
|  |  | student | visually interact with the software | I can more easily enter the unkowns | Requred
|  |  | developer | create a user friendly GUI | students can easily use the software | To Do
|  |  | student | have a user manual | to help with any questions I have with the software | Nice to have
|  |  | student | enter units | I don't have to do unit conversion myself | Nice to have
|  |  | student | enter variables from many disciplines | I can gain assistance with a broader range of physics problems | Nice to have
Sprint 1 - May 17 to May 23 |  |  | student | enter known variables | the calculator can produce as many unknowns as possible | Required
|  |  | developer | use recursion | to make a better algorithm for solving multiple unknowns | To Do
|  |  | team | create a presentation | for Midterm I | In Pogress
|  |  | developer | create a list of variables | I can decide which equations this software will solve | In Pogress
|  |  | developer | create an algorithm | I can solve for missing equations | In Progress
|  |  | team | create a catchy name for the app | I can market it to students | In Progress
|  |  | PO / SM | set up the sprint schedule | I can delegate tasks and make sure we are on track | In Progress
|  |  | developer | list references and sources | so that I give credit to those who created any code we use | In Progress
|  |  | developer | set up GitHub/Trello, etc. | so our team can communicate and share files | Done
|  |  | student | visually interact with the software | I can more easily enter the unkowns | Requred
|  |  | developer | create a user friendly GUI | students can easily use the software | In Progress
| Task # | Developer | As a/an | I/we want to… | so that… | Priority
Sprint 2 - May 24 to June 6 |  |  | student | enter known variables | the calculator can produce as many unknowns as possible | Required
| 1 | Chris | developer | write the code to solve for acceleration | it can be integrated into the generic algorithm | Done
| 2 | Steven J | developer | write the code to solve for velocity | it can be integrated into the generic algorithm | Done
| 3 | Chris | developer | write the code to solve for time | it can be integrated into the generic algorithm | Done
| 4 | Matt | developer | write the code to solve for displacement | it can be integrated into the generic algorithm | Done
| 5 | Dustin | developer | create a generic algorithm | I can solve problems, with entered variables | Done
| 6 |  | developer | list references and sources | so that I give credit to those who created any code we use | Done
| 7 |  | PO / SM | set up the sprint schedule | I can delegate tasks and make sure we are on track | Done
| 8 |  | team | create a presentation | can succeed on Midterm I | Done
| 9 |  | developer | set up GitHub/Trello, etc. | so our team can communicate and share files | Done
| 10 |  | team | create a catchy name for the app | I can market it to students | Done
| 11 |  | developer | create a list of variables | I can decide which equations this software will solve | Done
| - |  | developer | use recursion | to make a better algorithm for solving multiple unknowns | Dropped
|  |  | student | visually interact with the software | I can more easily enter the unkowns | Requred
| 12 | Steve C | developer | create a user friendly GUI | students can easily use the software | Done
| 13 | Steve C | developer | centralize all functions into one button | students can more easily use the calculator | Done
| 14 | Steve C | developer | create a method to save entries | students can easily reuse the same variable values | Done
| 15 | Steve C | developer | create a menu bar | students can save their projects, access credits, help, etc. | Done
|  |  | student | have a user manual | I can gain assistance with a broader range of physics problems | Nice to have
| 16 |  | developer | create a help page / menu | students can learn how the software works | Done
| Task # | Developer | As a/an | I/we want to… | so that… | Priority
Sprint 3 - June 7 to June 20 |  |  | student | enter known variables | the calculator can produce as many unknowns as possible | Required
| 1 |  | developer | refine the algorithm to keep solving | I can solve all problems possible, with known variables | In Progress
| 2 |  | developer | test the algorithm and eliminate bugs | the program will wok as intended | In Progress
| 3 | Steve C | developer | add negative numbers to error checker | students can enter negatives | In Progress
| 4 | Chris | developer | write the code to solve for acceleration | it can be integrated into the generic algorithm | Done
| 5 | Steven J | developer | write the code to solve for velocity | it can be integrated into the generic algorithm | Done
| 6 | Chris | developer | write the code to solve for time | it can be integrated into the generic algorithm | Done
| 7 | Matt | developer | write the code to solve for displacement | it can be integrated into the generic algorithm | Done
| 8 | Dustin | developer | create a generic algorithm | I can solve problems, with entered variables | Done
| 9 |  | developer | list references and sources | so that I give credit to those who created any code we use | Done
| 10 |  | PO / SM | set up the sprint schedule | I can delegate tasks and make sure we are on track | Done
| 11 |  | team | create a presentation | can succeed on Midterm I | Done
| 12 |  | developer | set up GitHub/Trello, etc. | so our team can communicate and share files | Done
| 13 |  | team | create a catchy name for the app | I can market it to students | Done
| 14 |  | developer | create a list of variables | I can decide which equations this software will solve | Done
| - |  | developer | use recursion | to make a better algorithm for solving multiple unknowns | Dropped
|  |  | student | visually interact with the software | I can more easily enter the unkowns | Requred
| 15 | Steve C | developer | create a user friendly GUI | students can easily use the software | Done
| 16 | Steve C | developer | centralize all functions into one button | students can more easily use the calculator | Done
| 17 | Steve C | developer | create a method to save entries | students can easily reuse the same variable values | Done
| 18 | Steve C | developer | create a menu bar | students can save their projects, access credits, help, etc. | Done
|  |  | student | have a user manual | I can gain assistance with a broader range of physics problems | Nice to have
| 19 |  | developer | create a help page / menu | students can learn how the software works | Done
|  |  | student | enter units | I don't have to do unit conversion myself | Nice to have
| 20 | Steve C | developer | add a unit warning message | students are reminded about entering proper units | In Progress
| 21 |  | developer | add code for unit conversion | students can use multiple units | In Progress
|  |  | student | enter variables from many disciplines | I can gain assistance with a broader range of physics problems | Nice to have
| 22 |  | developer | add in formulas for force and mass | sudents can use more physics | In Progress
Items added
Items removed